# TOGAF Phase F — Migration Planning

RUP Business Use Case Specification for AccelCQ AI-Driven Demo Platform for Confidential and Quantum Computing

## 1. Document Control

| Item | Description |
| --- | --- |
| Document Title | TOGAF Phase F – Migration Planning |
| Project | AccelCQ AI-Driven Demo Platform (Confidential & Quantum) |
| Version | 1.0 |
| Date | November 2025 |
| Author | Migration & Architecture Team, AccelCQ |
| Reviewed By | Enterprise Architecture Board |
| Approved By | Executive Leadership Team |

## 2. Purpose and Scope

This document defines the Migration Planning for the AccelCQ AI-driven Demo Platform for Confidential and Quantum Computing, per TOGAF ADM Phase F.

Purpose:
To design and schedule the practical migration of target architectures (Business, Data, Application, and Technology, Phases B–D) to operational deployment, balancing business priorities, risk, and readiness.

Scope:

- Migration waves, work packages, and priorities

- Transition states and dependencies

- Cutover and rollback strategies

- Risks, mitigation, resource planning, and governance

- Integration of Confidential and Quantum workloads into live platform

## 3. Business Use Case and Migration Drivers

### Use Case Summary

AccelCQ’s business must migrate from a legacy, partially manual demo environment to a fully automated, auditable, scalable platform, offering on-demand Confidential and Quantum Computing demos for clients.
Migration should minimize risk, maximize business continuity, and enable phased benefits realization.

Migration Drivers:

- Accelerated client onboarding and demo turnaround

- Seamless, auditable cutover to Confidential/Quantum-enabled delivery

- Zero downtime for active client-facing services

- Compliance and data integrity throughout migration

### PlantUML — Stakeholder & Actor Map for Migration

@startuml

title Migration Stakeholder and Actor Map

actor "Executive Sponsor" as Exec

actor "Product Owner" as PO

actor "Platform SRE" as SRE

actor "Migration Lead" as MigLead

actor "Security Officer" as Sec

actor "Client" as Client

rectangle "Migration Planning" {

usecase "Prioritize Work Packages"

usecase "Assess Cutover Risks"

usecase "Approve Transition State"

usecase "Communicate Migration Status"

usecase "Execute Rollback if Needed"

}

Exec --> "Approve Transition State"

PO --> "Prioritize Work Packages"

SRE --> "Communicate Migration Status"

MigLead --> "Assess Cutover Risks"

Sec --> "Execute Rollback if Needed"

Client --> "Communicate Migration Status"

@enduml

## 4. Migration Strategy Overview

### Principles

- Iterative, Wave-based Delivery: Deliver in incremental, testable steps with defined exit criteria.

- Minimum Viable Migration: Prioritize critical path capabilities (Confidential/Quantum workloads, audit, automation).

- Parallel Run & Shadowing: New and legacy run in parallel during cutover for critical demos.

- Continuous Verification: Metrics and checkpoints after each wave.

- Rollback Readiness: Each wave has automated rollback/restore procedures.

### PlantUML — Migration Waves

@startuml

title Migration Waves Overview

actor "Migration Lead" as MigLead

package "Migration Wave 1" {

component "Core Platform & Portal"

component "Legacy Integration"

}

package "Migration Wave 2" {

component "Confidential Compute Enablement"

component "Data Pipeline Migration"

}

package "Migration Wave 3" {

component "Quantum Integration"

component "Observability Enhancements"

}

package "Migration Wave 4" {

component "Security & Compliance Automation"

component "User Training & Change Mgmt"

}

MigLead --> "Core Platform & Portal"

MigLead --> "Confidential Compute Enablement"

MigLead --> "Quantum Integration"

MigLead --> "Security & Compliance Automation"

@enduml

## 5. Migration Work Package Inventory

### Major Work Packages

| WP# | Name | Description | Prerequisites |
| --- | --- | --- | --- |
| 1 | Core Platform & Portal Migration | Deploy Next.js portal, API Gateway, and orchestration layer | Infra provisioned |
| 2 | Legacy Integration Layer | Establish data sync/interfaces with legacy demo environment | Core platform live |
| 3 | Confidential Compute Node Pools | Deploy and configure AKS Confidential VMs, attestation | Core platform live |
| 4 | Data Pipeline & Storage Migration | Move demo/session data to new managed stores | Legacy integration live |
| 5 | Quantum API Integration | Deploy Quantum connector, job queue, API gateway integration | Confidential enabled |
| 6 | Observability & Audit Enhancements | Deploy OTel, Prometheus, SIEM, dashboards | Platform/compute live |
| 7 | Security & Compliance Automation | OPA/Gatekeeper, Key Vault, RBAC enforcement | Observability live |
| 8 | User Training, Documentation, Comms | Train teams, update docs, comms channels | All previous waves |

### PlantUML — Work Package Relationships

@startuml

title Migration Work Package Dependencies

component "Core Platform & Portal Migration"

component "Legacy Integration Layer"

component "Confidential Compute Node Pools"

component "Data Pipeline & Storage Migration"

component "Quantum API Integration"

component "Observability & Audit Enhancements"

component "Security & Compliance Automation"

component "User Training, Docs, Comms"

"Core Platform & Portal Migration" --> "Legacy Integration Layer"

"Core Platform & Portal Migration" --> "Confidential Compute Node Pools"

"Legacy Integration Layer" --> "Data Pipeline & Storage Migration"

"Confidential Compute Node Pools" --> "Quantum API Integration"

"Data Pipeline & Storage Migration" --> "Observability & Audit Enhancements"

"Quantum API Integration" --> "Observability & Audit Enhancements"

"Observability & Audit Enhancements" --> "Security & Compliance Automation"

"Security & Compliance Automation" --> "User Training, Docs, Comms"

@enduml

## 6. Migration Wave Planning & Timeline

### Migration Waves & Outcomes

| Wave | Key Deliverables | Duration | Exit Criteria |
| --- | --- | --- | --- |
| 1 | Portal/API live, basic demos available, legacy sync | 2 months | All legacy demos accessible via portal |
| 2 | Confidential Compute live, TEE jobs enabled, data moved | 2 months | All sensitive demos on enclave infra |
| 3 | Quantum API/connector deployed, new quantum demos | 2 months | At least 1 quantum demo in production |
| 4 | OTel, SIEM, dashboards, policy enforcement, training | 2 months | Automated alerts, compliance reporting |

### PlantUML — Migration Wave Timeline

@startuml

title Migration Wave Timeline

project PhaseF_MigrationWaves {

[Wave 1 - Core Platform] lasts 8 weeks

[Wave 2 - Confidential Compute] lasts 8 weeks

[Wave 3 - Quantum Integration] lasts 8 weeks

[Wave 4 - Observability, Security, Training] lasts 8 weeks

[Wave 2 - Confidential Compute] starts at end of [Wave 1 - Core Platform]

[Wave 3 - Quantum Integration] starts at end of [Wave 2 - Confidential Compute]

[Wave 4 - Observability, Security, Training] starts at end of [Wave 3 - Quantum Integration]

}

@enduml

## 7. Transition Architectures & States

### State 1: Legacy & MVP Coexistence

- Legacy manual portal and new automated portal both available

- Data synchronization jobs scheduled

- All existing clients can access via either path

### State 2: Confidential Workloads Onboarded

- All sensitive demos (marked as confidential) moved to TEE nodes

- Session data and logs written to new stores

- Rollback to legacy possible via toggling integration

### State 3: Quantum Workflows Activated

- New quantum demos available via IBM Qiskit integration

- Quantum session results appear in new artifact store

- User comms and training in progress

### State 4: Observability/Compliance Maturity

- All demo sessions monitored by OTel, logs shipped to SIEM

- Policy violations trigger auto-alerts

- Training and handover complete

## 8. Data Migration and Cutover Planning

### Data Migration Principles

- Immutable data (audit, logs) migrated with checksum validation

- Demo artifacts re-signed during migration

- Parallel data validation with rollback to legacy sources

- All migration steps logged for compliance

### PlantUML — Data Migration and Cutover Workflow

@startuml

title Data Migration and Cutover Workflow

actor "Migration Lead" as MigLead

database "Legacy Data Store"

database "New Metadata Store"

database "Artifact Store"

database "Audit Log"

component "Migration Script"

actor "Security Officer" as Sec

MigLead -> "Migration Script" : Launch Migration

"Migration Script" -> "Legacy Data Store" : Extract Data

"Migration Script" -> "New Metadata Store" : Transform/Load Metadata

"Migration Script" -> "Artifact Store" : Move/Sign Artifacts

"Migration Script" -> "Audit Log" : Log All Operations

Sec --> "Audit Log" : Validate Compliance

@enduml

## 9. Integration and Coexistence Approach

- API Versioning: Support both legacy and new API endpoints during transition

- Feature Flags: Use toggles to control user exposure to new/legacy systems

- Parallel Processing: Enable both old and new systems to process the same requests (shadowing) for select period

- Backout Plan: Instant re-routing to legacy endpoints on failure

### PlantUML — Integration and Coexistence

@startuml

title Integration and Coexistence Approach

actor "Client"

component "Legacy Portal"

component "New Portal"

component "API Gateway"

component "Feature Toggle Service"

database "Legacy Data"

database "New Data"

Client --> "Feature Toggle Service" : Query Routing

"Feature Toggle Service" --> "Legacy Portal" : If Legacy Demo

"Feature Toggle Service" --> "New Portal" : If Migrated Demo

"Legacy Portal" --> "Legacy Data"

"New Portal" --> "New Data"

@enduml

## 10. Cutover, Rollback, and Contingency Planning

### Cutover

- Cutover event scheduled for each migration wave

- All stakeholders notified, comms templates prepared

- Cutover window with parallel run and real-time monitoring

### Rollback

- Automated scripts to reverse data, restore previous version, and re-enable legacy endpoints

- Data integrity and completeness verified before public cutover

### Contingency

- Exception list for demos that cannot be migrated in time (with sunset/alternate process)

- Pre-agreed escalation contacts and support channels

### PlantUML — Cutover and Rollback Event Flow

@startuml

title Cutover and Rollback Flow

actor "Migration Lead" as MigLead

actor "Platform SRE" as SRE

actor "Product Owner" as PO

component "Feature Toggle Service"

component "Monitoring Dashboard"

component "Rollback Script"

MigLead -> "Feature Toggle Service" : Switch Routing to New Platform

SRE -> "Monitoring Dashboard" : Watch Health, Errors

PO -> "Monitoring Dashboard" : Confirm Acceptance

alt Failure Detected

SRE -> "Rollback Script" : Initiate Rollback

"Rollback Script" -> "Feature Toggle Service" : Revert Routing

end

@enduml

## 11. Risk Assessment and Mitigation

| Risk Area | Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| Data Loss | Data lost during migration | Low | High | Checksums, backups, validation, staged moves |
| Service Disruption | Portal/API outage on cutover | Med | High | Parallel run, feature toggles, instant rollback |
| Compliance Breach | Logs/artifacts missed | Low | High | Pre/post audits, SIEM, manual signoff |
| Incomplete Migration | Some demos not migrated | Med | Med | Exception list, comms, alternate process |
| User Readiness | Teams slow to adapt | Med | Med | Early training, support channels, documentation |

## 12. Resource and Skill Planning

| Role | Key Responsibilities | Required Skills |
| --- | --- | --- |
| Migration Lead | Orchestration, comms, risk mgmt | Project Mgmt, comms, tech |
| Platform SRE | Infra, monitoring, rollback | Kubernetes, cloud ops, OTel |
| Data Engineer | Data migration scripts, validation | SQL, Python, audit, security |
| Security Officer | Compliance, audit, policy review | Policy, compliance, SIEM |
| DevOps Engineer | CI/CD, GitOps, rollback automation | IaC, CI/CD, Kubernetes, cloud |
| Product Owner | Acceptance, user comms | Business analysis, comms |

### PlantUML — Resource and Skills Map

@startuml

title Resource and Skills Map

actor "Migration Lead"

actor "Platform SRE"

actor "Data Engineer"

actor "Security Officer"

actor "DevOps Engineer"

actor "Product Owner"

rectangle "Migration Project" {

"Migration Lead" -- "Orchestration"

"Platform SRE" -- "Monitoring"

"Data Engineer" -- "Data Migration"

"Security Officer" -- "Compliance"

"DevOps Engineer" -- "Automation"

"Product Owner" -- "Acceptance"

}

@enduml

## 13. Governance and Communication

- Weekly Steering Meetings: All stakeholders

- Daily Standups: Migration team

- Migration Dashboard: Real-time progress, health, risk indicators

- Stakeholder Notifications: Pre/post wave comms, cutover windows, exception alerts

- Approval Gates: Each wave subject to formal go/no-go review

## 14. Migration Success Criteria and KPIs

| KPI | Target |
| --- | --- |
| Zero data loss incidents | 100% |
| Portal/API downtime | < 15 min per cutover |
| Demo provisioning time | < 5 min post-migration |
| All confidential demos on TEE | 100% |
| Quantum demo availability | ≥ 1 production use case |
| Training completion | 100% migration team |
| Compliance audit pass | 100% |

## 15. Traceability Matrix (RUP Mapping)

| RUP Artifact | TOGAF Migration Planning Section |
| --- | --- |
| Business Use Case Model | 3, 5, 7 |
| Migration Work Packages | 5, 6 |
| Migration Wave Plan | 6, 7 |
| Data Migration/Cutover | 8, 10 |
| Risk Register | 11 |
| Resource Plan | 12 |
| Communication Plan | 13 |
| Success Criteria | 14 |

## 16. Glossary

| Term | Definition |
| --- | --- |
| Migration Wave | Logical group of work packages deployed together |
| Cutover | Event where new system takes over from old |
| Shadowing | Both systems run in parallel for verification |
| Feature Toggle | Mechanism to enable/disable features dynamically |
| Backout Plan | Pre-defined rollback strategy in case of migration failure |
| SIEM | Security Information and Event Management platform |

## 17. Conclusion

This Phase F Migration Planning document defines a robust, low-risk, phased approach for delivering the next-generation AccelCQ AI-Driven Demo Platform.
With clear migration waves, work package dependencies, cutover and rollback protocols, KPIs, and a detailed stakeholder, resource, and risk plan, AccelCQ is set to achieve its Confidential and Quantum Computing objectives without business disruption—while maintaining full compliance, auditability, and user trust.